## Self Publishing Plan
STEPS | DETAILED TASKS | START | TARGET | TEMPLATES | NOTES
CREATE CONTENT | COVER |  |  | Cover Template in Photoshop
| Prep |  |  |  | * What tools will you use? * What formats do these tools accepts?
Review notes from sessions
| Get Photoshop |  |  |  | Purchased through Creative Cloud
Photoshop tutorials
| Try out some of my existing pictures |  |  |  | Determine if I need new photos
| Look at other books in genre |  |  |  | online and in bookstore
Setup
| Determine Layout Dimensions |  |  | DIMENSION SPREADSHEET?
Setup Grid
Design
Photo
Hue and Saturation
Title (Front and Spine)
Cover Blurb
ISBN / Bar Code
Author Biography
MANUSCRIPT
| Finish Content |  |  |  | Put everything in there that you want !!!
Core Content
Optional Content
Inside Cover
Pictures
Quotes
Maps
Additional Content
Title Page
Copyright Page
Description
Author Biography
Dedication Page
Acknowledgements
Preface
Prologue
| Editing |  |  | Sample spreadsheet ? OR TIP SHEET
Identify Editing Options
Research Editing Options
Compare Editing Options
| Finalize editing agreement |  |  |  | Editing should include three passes.
| Format Manuscript |  |  | FORMAT GUIDELINES
Set up Page Guidelines
Choose Font
ASSEMBLY | EBOOK |  |  | WORKFLOW PROCESS TEMPLATE
Determine Platforms to distribute on
| Understand how various devices work |  |  |  | Went to several stores and looked
KDP Prep
Read Publishing Guidelines
Set up account
Set up test environment
| Perform a first test run |  |  |  | Need at least a test manuscript file
iBooks Prep
Read Publishing Guidelines
Install tools (iAuthor & Producer)
Test out iAuthor
Set up test environment
Perform first test run
Overview of Producer
Book Price
Additional Metadata
Finalize
| PRINT |  |  | WORKFLOW PROCESS TEMPLATE
| Choose Printer |  |  |  | Examples: Create Space, Lightening Source, Blitzprint, Blurb.ca, Local Printers
Identify Options for Printing
| Research each Option |  |  | SPREADSHEET ON PRINTING? | Identify important information for each option
Compare Options
Set Up
Create Account
Setup Test Environment
| Perform Test Run |  |  |  | Helps identify file types and formats
| ISBN |  |  |  | Canadian ISBNs are free, takes about 10 days, Depending on printer might not need
Book Price
Additional Metadata
Determine Categories
Determine Keywords
Contributors
Description
Finalize - convert to final format
PUBLISH | eBook
KDP Prep
Agreement (terms and conditions)
Royalties
Tax
Bank Fees
iBooks Prep
Agreement (terms and conditions)
Royalties
Tax
Bank Fees
PRINT
Proofs - Repeat until no further changes required
| Order First Round Proofs |  |  |  | 1, 2 or even 3 weeks depending on where you order from
Review first round proofs
Updates to manuscript and cover
Re-Order Proofs
Order final copies
LAUNCH | LAUNCH |  |  |  | Look at Meet the Public Look at Business Side of Launching your Book
Plan Launch
Venue
Guest List
Create Invitation
Distribute Invitation
Pre-orders for books
Finalize Publishing
| Set up Print on Demand (Blurb) |  |  |  | (Gum Road), Blurb, my website
Publish e-books
Advertise
| See Marketing |  |  |  | Done - plug more AFTER launch
MARKETING | MARKETING
Leverage Network
Social Media
City Clubs, Groups, Networks
Identify Your Audience
Signings
Readings
Events
Cards
Flyers, Pamphlets, Signs
Website
Newsletter
Author Page
Book Promotions / Giveaways